## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Introduction & Problem Understanding (Stock & ETF Signals) | MUST HAVE | No Dependency | Mosra Sanjana Reddy | 3- Completed
S1 | S1 | US-002 | Workflow Design & Architecture Planning (ML + APIs + Dashboard) | MUST HAVE | Lucidchart / Draw.io | Mosra Sanjana Reddy | 3- Completed
S2 | S2 | US-003 | Environment Setup & API Integration (Yahoo Finance / Alpha Vantage) | MUST HAVE | Python, APIs | Mosra Sanjana Reddy | 3- Completed
S2 | S2 | US-004 | Data Cleaning & Feature Engineering for Market Data | MUST HAVE | Pandas, NumPy | Mosra Sanjana Reddy | 3- Completed
S3 | S3 | US-005 | ML Model Development (Random Forest, LSTM, Gradient Boosting) | MUST HAVE | Scikit-learn, TensorFlow | Mosra Sanjana Reddy | 3- Completed
S4 | S4 | US-006 | Signal Generation Logic (Buy/Sell/Hold Predictions) | MUST HAVE | ML Models | Mosra Sanjana Reddy | 3- Completed
S5 | S5 | US-007 | Backtesting Engine Implementation (Historical Data Testing) | MUST HAVE | Historical Data APIs | Mosra Sanjana Reddy | 2- In Progress
S6 | S6 | US-008 | Performance Metrics Calculation (Sharpe Ratio, Drawdown, Win Rate) | SHOULD HAVE | Backtesting Module | Mosra Sanjana Reddy | 2- In Progress
S7 | S7 | US-009 | Real-Time Alert System (Email / Slack Notifications) | SHOULD HAVE | SMTP / Slack API | Mosra Sanjana Reddy | 2- In Progress
S8 | S8 | US-010 | Dashboard Development (Streamlit / Dash Visualization) | MUST HAVE | Streamlit / Plotly | Mosra Sanjana Reddy | 2- In Progress
S9 | S9 | US-011 | Integration of All Modules (End-to-End Workflow) | MUST HAVE | All Modules | Mosra Sanjana Reddy | 2- In Progress
S10 | S10 | US-012 | Testing, Deployment & Final Presentation (Render/Cloud) | MUST HAVE | Render / Cloud | Yash Kumar Sahu | 2- In Progress
Note on F1: ====== ID#AAAB2g0hvBY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 39 | 2 | 2 | 3.5 | 5 | 7 | 5.5 | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Project understanding & planning | 2026-02-02 | 16-02-2026 | Mosra Sanjana Reddy | Build | 3- Completed | 6 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Research stock & ETF signals | 2026-02-02 | 2026-07-02 | Palepu Sri Mahalakshmi | Coding | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | System architecture design | 2026-10-02 | 15-02-2026 | Mosra Sanjana Reddy | Design | 3- Completed | 8 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-002 | T-004 | Workflow diagram creation | 2026-10-02 | 16-02-2026 | Susekha P | Design | 3- Completed | 5 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-005 | API exploration & setup | 2026-12-02 | 18-02-2026 | Lokesh Avulapati | Integration Test | 3- Completed | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-002 | T-006 | Documentation preparation | 14-02-2026 | 20-02-2026 | Zakkireddy Srihitha Reddy | System Test | 3- Completed | 5 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-002 | T-007 | UI setup | 15-02-2026 | 22-02-2026 | Yash Kumar | Unit Test | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAB2g0hvBA Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB2g0hvBg Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB2g0hvA0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB2g0hvAw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB2g0hvBM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB2g0hvBQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB2g0hvBc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB2g0hvA4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB2g0hvAg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB2g0hvAo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB2g0hvBI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB2g0hvAk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB2g0hvAs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB2g0hvBE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB2g0hvBU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB2g0hvA8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB2g0hvAc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Initial confusion in project understanding | Reviewed project documentation
S1 | Day 2 | Difficulty in identifying data sources | Explored financial APIs like Yahoo Finance
S1 | Day 3 | Lack of clarity in ETF concepts | Studied online tutorials and references
S1 | Day 4 | Understanding trading signals was complex | Referred to articles and examples
S1 | Day 5 | Difficulty in mapping requirements | Broke down problem into smaller tasks
S1 | Day 6 | Selecting proper tools for design | Chose Draw.io for workflow creation
S1 | Day 7 | Minor confusion in architecture design | Revised system components
S1 | Day 8 | Difficulty in structuring workflow | Improved diagram step-by-step
S1 | Day 9 | Time management issue | Allocated fixed hours daily
S1 | Day 10 | Small design inconsistencies | Refined architecture
S1 | Day 11 | No major issues | Continued work smoothly
S1 | Day 12 | No major issues | Progressed as planned
S1 | Day 13 | Minor doubts in final design | Cross-checked design
S1 | Day 14 | No issues | Completed sprint successfully

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-01-02 | 2026-05-03 | Mosra Sanjana Reddy | Start better system design planning | Stop delaying critical decisions | Continue leading core development | Improved architecture and coordination
2 | S1 | 2026-01-02 | 2026-05-03 | Palepu Sri Mahalakshmi | Start deeper API understanding | Stop relying only on basic data | Continue consistent research | Explored multiple financial APIs
3 | S1 | 2026-01-02 | 2026-05-03 | Lokesh Avulapati | Start improving backend integration | Stop minor debugging delays | Continue API development work | Fixed API issues and improved integration
4 | S1 | 2026-01-02 | 2026-05-03 | Susekha P | Start enhancing UI design quality | Stop basic UI layouts | Continue frontend development | Improved dashboard design
5 | S1 | 2026-01-02 | 2026-05-03 | Zakkireddy Srihitha Reddy | Start detailed documentation | Stop minimal documentation | Continue testing support | Created structured documentation
6 | S1 | 2026-01-02 | 2026-05-03 | Yash Kumar | Start learning UI basics | Stop inconsistent work | Continue assisting team | Completed basic UI tasks